DSO INTERNATIONAL REFRESHER COURSE

ICRAF HQ, Nairobi 7-23 November 2001

# LOGISTICS CHECKLIST – status date

| ## ACTIVITY | RESPONSIBLE | BY WHEN/ COMMENTS |
| --- | --- | --- |
| PRE-COURSE ARRANGEMENTS |  |  |
| - Nomination letter & package | EK | done |
| - Applications - filing | EK | ongoing |
| - Budget & expenditure | EK + JB | continuous |
| - Programme content & resource persons | JB + JA | ongoing |
| - Field visits Rift Valley – Western Kenya | JA | End September |
| - Selection | JB + T&E | End September |
| - Confirmations + info package | EK | End September - October |
| - International travel arrangements (TAs, bookings, follow-up) | Travel Unit with EK/RM |  |
| - Liaison with Protocol Office to facilitate arrivals | EK |  |
| - Liaison with DGs Office on opening & closing | JB | Course opening |
| - Local transport (participants & resource persons) - Airport - Daily - Field visit (car-air return) | JA with John Bruce and/or Travel ICRAF? Tour company (?) Tour company | course |
| - Hotel booking (B&B arrangement) – Nairobi - Hotel booking (Kisumu) 14-15 November | RM + Intercon JA (field visit) + RM or EK | asap |
| - Catering: - Water in training room(s) - lunches - coffee breaks - 2 social functions (+invitations) | RM with EK RM NAS NAS Caterer + Carnivore |  |
| - Name tags | EK |  |
| - Conference bags & binder ordering | EK + JB | Logos + binders (25) |
| - Stationery (usual set participants and training rooms) | EK/RM | course |
| - Registration and claims form | RM/EK | course |
| - Per diem payments | FINAD + RM | course |
| - Medical insurance | N/A | N/a |
| - Training materials - Collect – collate - Copying - Binding (binders) - Distribution ( | JB EK + photocopying EK + messenger(s) RM + messenger(s) | Ongoing October October Course |
| - Training rooms and facilities - Bookings (conference hall + smaller rooms) - Equipment - Decoration | RM + EK + J. Kiio + Sammy RM | Asap Course |
| - Certificates of participation | JB + EK + CM | Course |
| - Welcome letter + practical info + identification letter | JB + EK | Pre-course |
| ## DURING THE COURSE |  |  |
| - Registration desk (bags, binders, forms, nametags,…) | RM/EK |  |
| - Secretarial services (communications, typing,…) | EK + RM (JB + JA) | (no phones/e-mail) |
| - Handout reproduction and distribution (photocopying) | EK/JB |  |
| - Arrange for a group picture | EK + A N |  |
| - Messenger services (?) | RM |  |
| - Course & TM evaluation - Form development - Distribution & collection - Analysis | JB + PT |  |

Comments:

- JA to assist on field visits, impact assessment, backstopping

- A list of (social) options for the 2 Sundays needs to be developed. Participation at participant expense, ICRAF only facilitates.  (RM to propose)

- DSA at 25 US$ pp/pd to cover meals and out of pocket expenses

- Conference hall arrangement is 8 ‘round’ tables of 5 seats each plus 20 back row seats for observers. 3 or 4 smaller rooms needed during the last week to accommodate group work.

- No medical insurance but assistance for specific cases

- No special banking facilities required

- No additional caterer for daily lunches while at ICRAF. NAS to prepare special menus.

- Those responsible for specific activities to all relevant copy info to organizing committee (JB+JA+RM+EK)